DeskOf Build Companion

Phased Implementation Plan

Kinetiks AI - April 2026

Total estimated build: 8 phases, ~69-87 days

Prerequisite: Kinetiks ID Phase 6+ complete. Cortex operational.

# Build Sequence Overview

DeskOf builds in 8 phases. Each phase produces a usable increment. The first three phases deliver the core loop (discover, write, post). Phases 4-6 add the intelligence and tracking layers. Phases 7-8 add gamification and polish.

The critical dependency is the Research Spike (Phase 0) which validates the LLM citation prediction model before investing in the full discovery engine. If the spike shows insufficient signal, the discovery engine launches with a simpler scoring model and the citation prediction layer is deferred.

# Phase 0: Research Spike - Citation Prediction Model

Duration: 5-7 days. This phase runs before any product build. Its purpose is to validate whether LLM citation probability can be predicted from thread attributes.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 0.1 | Build Reddit thread scraper - collect 3,000+ threads across target verticals (growth, SaaS, startups, marketing) going back 12 months. Store thread metadata: subreddit, title, body, score, comment count, age, top reply structure, Google index status. | 2 | None |
| 0.2 | Build LLM citation checker - for each thread, extract core question, run through ChatGPT, Perplexity, Gemini, Claude APIs. Parse responses for source URLs, thread references, brand mentions, paraphrased content. | 2 | 0.1 |
| 0.3 | Build labeled dataset - join thread attributes with citation results. Produce binary labels (cited/not-cited) per model and aggregate. | 1 | 0.2 |
| 0.4 | Train and evaluate initial model - logistic regression or lightweight gradient boost. Identify top predictive features. Document findings and go/no-go recommendation. | 2 | 0.3 |

Phase 0 Exit Criteria

- Labeled dataset of 3,000+ threads with citation status across 4 LLM platforms

- Initial prediction model with documented accuracy, precision, recall

- Feature importance ranking confirming or rejecting hypothesis about thread structure, subreddit authority, Google indexing, question format

- Go/no-go document: if AUC > 0.65, proceed with citation prediction as core feature. If below, proceed with simplified scoring and defer citation prediction to longitudinal data.

# Phase 1: Foundation

Duration: 10-12 days. App scaffolding, auth, database, Reddit integration, Quora scraper.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 1.1 | Scaffold Next.js app in apps/deskof/ within Kinetiks Turborepo. Configure Tailwind, Geist fonts, shared packages. | 1 | None |
| 1.2 | Integrate Kinetiks ID auth - shared .kinetiks.ai cookie, middleware, session management. Verify cross-app auth works. | 2 | 1.1 |
| 1.3 | Create Supabase schema - all deskof_ prefixed tables per CLAUDE.md spec. RLS policies. Migrations. | 2 | 1.1 |
| 1.4 | Reddit OAuth integration - connect flow, token storage, scope management (read, submit, history). Account import. | 2 | 1.2, 1.3 |
| 1.5 | Build Reddit API client - abstraction layer with rate limiting, exponential backoff, error handling. Thread fetching, comment reading, reply posting. | 2 | 1.4 |
| 1.6 | Build Quora scraper client - Playwright-based headless scraper for question discovery, answer extraction, and score tracking. Aggressive rate limiting (20 req/min). Robust selector fallbacks for markup changes. Store in deskof_threads with platform: quora. | 3 | 1.3 |
| 1.7 | Build platform abstraction layer - shared interface for thread fetching, reply posting, and tracking that Reddit and Quora clients both implement. Reddit posts via API, Quora uses browser handoff (copy to clipboard + open URL). | 1 | 1.5, 1.6 |
| 1.8 | Floating pill connector integration (shared Kinetiks UI component). | 1 | 1.2 |

Phase 1 Exit Criteria

- App loads at deskof.kinetiks.ai with Kinetiks ID auth

- Reddit account connected with OAuth, tokens stored securely

- Reddit API client can fetch threads, read comments, and post replies

- Quora scraper can discover questions, extract answers, and track scores

- Platform abstraction layer enables Scout to treat Reddit and Quora threads identically

- Database schema deployed with all core tables

# Phase 2: Core Write Loop

Duration: 10-12 days. The Write tab, opportunity cards, reply editor, and posting.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 2.1 | Build Operator Profile foundation in packages/cortex/ - types, builder, expertise tier structure. Manual setup flow for initial profile (user fills in top 5 expertise topics and personal interests). | 3 | 1.3 |
| 2.2 | Build Scout v1 - keyword-based thread discovery against Reddit API and Quora scraper via platform abstraction layer. Subreddit and Quora topic monitoring for configured topics. Thread metadata extraction and storage. | 3 | 1.7 |
| 2.3 | Build basic match scoring - expertise fit (keyword overlap with Operator Profile) and thread freshness. No timing model or citation prediction yet. | 2 | 2.1, 2.2 |
| 2.4 | Build Write tab UI - opportunity card stack. Single card view showing thread title, platform badge (Reddit/Quora), match score, context snippet. Accept/skip interaction with skip reason selector. | 2 | 2.3 |
| 2.5 | Build reply editor with dual posting flow - text input with character count, thread context sidebar. Reddit: post via API. Quora: copy to clipboard + open question URL in browser + user confirms posting. | 2 | 2.4, 1.7 |
| 2.6 | Build Track selector - minimal/standard/hero picker. Persisted in deskof_operator_tracks. Controls opportunity queue depth. | 1 | 2.4 |

Phase 2 Exit Criteria

- User can open Write tab, see opportunity cards from both Reddit and Quora, skip with reasons

- User can write a reply and post it to Reddit through the app

- User can write a reply and post it to Quora via browser handoff (clipboard + open URL + confirm)

- Track selection works and controls how many cards surface

- Core write loop functional end-to-end on both platforms, even if intelligence is basic

# Phase 3: Quality Gate

Duration: 5-7 days. Lens operator - the quality gate that protects users from bad posts.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 3.1 | Build self-promotion ratio tracker - analyze user's posting history across connected subreddits, maintain rolling 30-day ratio of promotional vs non-promotional posts. | 2 | 2.5 |
| 3.2 | Build gate check engine - self-promotion ratio check, link presence detection, redundancy check (compare reply against existing top answers in thread), tone analysis via LLM. | 3 | 3.1 |
| 3.3 | Build gate UI - inline gate results below reply editor. Clear/advisory/blocked status. Specific recommendations per check. Override capability for advisories. | 2 | 3.2 |
| 3.4 | Server-side gate validation - re-run gate checks on post submission to prevent client-side bypass. Block posting if server-side blocked. | 1 | 3.2, 3.3 |

Phase 3 Exit Criteria

- Quality gate runs on every reply before posting

- Self-promotion ratio calculated and enforced

- Gate shows clear/advisory/blocked with specific recommendations

- Server-side validation prevents bypass

- User can override advisories but cannot override blocks

# Phase 4: Discovery Engine Intelligence

Duration: 10-12 days. Upgrading Scout from keyword matching to the full scoring model.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 4.1 | Build timing model - upvote velocity tracking, comment arrival rate, OP engagement detection. Predict optimal reply window per thread. | 3 | 2.2 |
| 4.2 | Integrate citation prediction model (from Phase 0 research spike). Thread-level LLM citation probability scoring. | 2 | 0.4, 2.2 |
| 4.3 | Build answer gap detection - analyze existing replies in thread, identify missing perspectives, match gaps to operator expertise. | 3 | 2.1, 2.2 |
| 4.4 | Build anti-signal filtering - astroturf detection (account age patterns, posting patterns), community hostility scoring, cold-entry warnings, redundancy detection. | 2 | 2.2 |
| 4.5 | Build opportunity cost budgeting - rank opportunities against each other within track budget, surface only top-N. | 1 | 4.1, 4.2, 4.3, 4.4 |
| 4.6 | Build suggested angle generation - LLM-powered one-line suggestion based on thread context + operator expertise + answer gaps. NOT a draft reply. | 2 | 4.3, 2.1 |

Phase 4 Exit Criteria

- Opportunities scored with full composite: expertise fit, timing, citation probability, answer gap, anti-signal

- Suggested angles are specific and contextual, not generic

- Opportunity queue respects track budget and ranks by expected value

- Quality of surfaced opportunities is measurably better than keyword-only matching

# Phase 5: Reply Tab and Thread Management

Duration: 7-9 days. The Reply tab - active thread management, triage, sentiment.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 5.1 | Build reply monitoring - poll Reddit API for responses to user's posted replies. Store in deskof_reply_tracking. | 2 | 2.5 |
| 5.2 | Build triage engine - classify incoming replies as Engage/Acknowledge/Ignore/Opportunity using LLM analysis of reply content and thread context. | 3 | 5.1 |
| 5.3 | Build Reply tab UI - list of active threads with triage badges, reply preview, sentiment indicator. Tap to expand thread context and respond. | 2 | 5.2 |
| 5.4 | Build sentiment analysis - track thread sentiment over time using LLM classification. Flag when threads the user participated in are turning negative. | 2 | 5.1 |
| 5.5 | Build triage learning loop - track when user overrides triage recommendations. Feed overrides back into triage model. | 1 | 5.3 |

Phase 5 Exit Criteria

- Reply tab shows all active threads with current triage status

- Triage recommendations are accurate and actionable

- Sentiment shifts flagged proactively

- User can respond to replies directly from the Reply tab

# Phase 6: Reputation Tab and Tracking Engine

Duration: 10-12 days. Pulse operator - the tracking engine and Authority Score.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 6.1 | Build immediate tracking (0-24h) - removal detection, upvote velocity, OP engagement, early reply engagement. | 2 | 2.5 |
| 6.2 | Build short-term tracking (1-4 weeks) - thread Google ranking check, reply position tracking, secondary engagement detection. | 2 | 6.1 |
| 6.3 | Build medium-term tracking (1-3 months) - LLM citation checks. Scheduled jobs running thread questions through LLM APIs and parsing for citations. | 3 | 6.2 |
| 6.4 | Build long-term tracking (3+ months) - organic brand mention detection, branded search correlation via GSC integration, authority trajectory. | 2 | 6.3 |
| 6.5 | Build Authority Score computation - composite score from reach, resonance, reverberation. Per-topic scoring. Historical trend. | 2 | 6.1-6.4 |
| 6.6 | Build Reputation tab UI - Authority Score display with trend chart, time horizon drill-downs, platform health dashboard, cooling recommendations. | 3 | 6.5 |
| 6.7 | Build platform health monitoring - self-promotion ratio display, per-subreddit standing, posting frequency vs norms, risk indicators. | 1 | 3.1, 6.6 |

Phase 6 Exit Criteria

- Authority Score calculated and displayed per expertise area

- All four time horizons tracking and surfacing data

- LLM citation checks running on schedule

- Platform health monitoring with proactive cooling recommendations

- Reputation tab provides complete performance picture

# Phase 7: Personal Interest Engine and Operator Profile Intelligence

Duration: 5-7 days. Mirror operator - dynamic profile building and personal engagement.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 7.1 | Build content ingestion for Mirror - import user's blog posts, newsletter content, product docs. Extract topics, voice patterns, expertise signals. | 3 | 2.1 |
| 7.2 | Build dynamic expertise tier assignment - Mirror analyzes ingested content + posting history to automatically assign Core Authority / Credible Adjacency / Genuine Curiosity per topic. | 2 | 7.1 |
| 7.3 | Build personal interest surfacing - Scout parallel pipeline for non-professional threads matching operator's personal interests. | 2 | 7.2, 2.2 |
| 7.4 | Build crossover detection - identify threads where personal and professional interests intersect. Prioritize these in the opportunity queue. | 1 | 7.3 |
| 7.5 | Build personal engagement cadence tracking - monitor ratio of personal vs professional posts, nudge when personal engagement is low. | 1 | 7.3 |

Phase 7 Exit Criteria

- Operator Profile builds dynamically from content and behavior, not just manual input

- Personal interest threads surface in the Write tab alongside professional opportunities

- Crossover opportunities detected and prioritized

- System nudges when personal engagement cadence drops

# Phase 8: Gamification, MCP, and Polish

Duration: 7-9 days. Levels, streaks, MCP tools, and production polish.

| Task | Description | Est. Days | Depends On |
| --- | --- | --- | --- |
| 8.1 | Build level progression system - Observer through Referenced. Level computed from Authority Score milestones and engagement history. | 2 | 6.5 |
| 8.2 | Build streak and consistency mechanics - top-3 reply streaks, healthy ratio weeks, month-over-month growth tracking. | 1 | 6.5 |
| 8.3 | Build MCP tools - deskof_get_opportunities, deskof_check_draft, deskof_get_authority, deskof_get_thread_status, deskof_get_platform_health, deskof_post (with human confirmation enforcement). | 3 | All prior phases |
| 8.4 | Build discovery engine feedback loop - track skipped opportunities' outcomes, adjust scoring weights based on actual performance data. | 2 | 4.5, 6.1 |
| 8.5 | Production polish - loading states, error handling, empty states, onboarding flow, settings, notifications. | 3 | All prior phases |
| 8.6 | Security audit - verify human-only publishing constraint at all layers, API key scoping, RLS policies, OAuth token security. | 1 | All prior phases |

Phase 8 Exit Criteria

- Level progression and streaks visible in Reputation tab

- All MCP tools operational and documented

- Discovery engine self-improving from outcome data

- Security audit passed with human-only publishing verified

- App production-ready

# Build Summary

| Phase | Focus | Days | Cumulative |
| --- | --- | --- | --- |
| Phase 0 | Research Spike | 5-7 | 5-7 |
| Phase 1 | Foundation | 10-12 | 15-19 |
| Phase 2 | Core Write Loop | 10-12 | 25-31 |
| Phase 3 | Quality Gate | 5-7 | 30-38 |
| Phase 4 | Discovery Intelligence | 10-12 | 40-50 |
| Phase 5 | Reply Tab | 7-9 | 47-59 |
| Phase 6 | Reputation + Tracking | 10-12 | 57-71 |
| Phase 7 | Personal + Profile Intel | 5-7 | 62-78 |
| Phase 8 | Gamification + MCP + Polish | 7-9 | 69-87 |

Total estimated: 69-87 days. Can be compressed with parallel execution of independent phases (e.g., Phase 5 and Phase 6 can run concurrently after Phase 4).

# Parallelization Opportunities

- Phase 0 (Research Spike) can run in parallel with Phase 1 (Foundation) - different workstreams

- Phase 5 (Reply Tab) and Phase 6 (Reputation) can run concurrently after Phase 4

- Phase 7 (Mirror/Profile) can start alongside Phase 6 since it depends on Phase 2 foundations

- With maximum parallelization, critical path reduces to approximately 52-58 days

# Risk Factors

- Reddit API: rate limits, TOS changes, or deprecation could impact core functionality. Mitigation: build thick abstraction layer, stay well within rate limits, monitor Reddit developer changelog.

- Citation model quality: Phase 0 may show insufficient signal. Mitigation: the product works without citation prediction (it just becomes a less differentiated discovery tool). Citation prediction can be added when longitudinal data is available.

- Quora scraping fragility: no official API means scraping can break any time Quora changes markup. Mitigation: Playwright-based scraper with multiple selector fallbacks, automated tests that detect breakage, and graceful degradation (if Quora scraping fails, DeskOf continues to work with Reddit-only opportunities while scraper is repaired).

- LLM API costs: citation checking across 4 models at scale could become expensive. Mitigation: batch checks, reduce frequency for older threads, prioritize high-score threads for checking.